ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Municipality of Kocani

## Country background

Through cooperation with associations of municipalities, numerous local authorities from the North Macedonia laid out their sustainable urban mobility strategy and made first steps toward a people-centered urban mobility system. The endeavour was facilitated by several organizations. Several municipalities have worked intensively in the past year on the promotion of sustainable urban mobility.

Some of the local authorities interested to promote sustainable urban mobility and introduce concrete measures implemented pilot projects, received trainings and produced sustainable urban mobility plans (SUMPs) or sustainable urban mobility solutions.

The new sustainable urban mobility strategy opens the way for cleaner and more sustainable ways of transportation in the region: more walking, cycling, public transportation, developing new concepts of usage and ownership of cars, utilization of new smart technologies and adoption of sustainable city logistics.

# OBJECTIVES & EXPECTED OUTPUTS

Cities are at the forefront of today’s greatest challenges and opportunities. Climate change, intergenerational gaps and digital disruption are just some common turning points for European cities. And yet, cities are also home to cultural diversity, economic opportunities and essential services. It’s by sharing experiences with other cities that we can harness the many opportunities of sustainable urban development. This is where URBACT comes in.

URBACT promotes integrated development to support cities implement horizontal and vertical policy integration. Positive change can best be made when local authorities collaborate with different levels of governance (regional, national, EU) –vertical integration – and when they tackle challenges and problems in a holistic way that considers environmental, economic, and social dimensions at the same time – horizontal integration.

URBACT has developed a series of processes and tools, as a part of the URBACT Method. It encourages cities to re-think centralised governance structures and shift towards more inclusive and holistic models. URBACT’s participatory approach recognises that sustainable urban development is driven by action-oriented strategies, which are co-created and implemented with local people.

Through transnational URBACT networks, programme and national level capacity-building activities, URBACT aims to increase the capacity in integrated and participatory approaches of urban practitioners and local stakeholders that are part of the URBACT networks.

## Overall objective

The overall objective (Impact) to which this action contributes is :

More sustainable urban areas.

## Specific objective(s)

The specific objective (Outcome) of this contract is as follows:

- successful implementation of the project and foreseen tender procedures

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

Formulated all necessary project implementation documents (progress reports, financial documentations etc)

Tender Dossier for SERVICE Development of Sustainable Urban Mobility Plan (SUMP)

Tender Dossier for SUPPLY - Supply

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Good cooperation between all parties involved in the contract completion.

## Risks

No significant risks have been identified for the completion of the contract

# SCOPE OF THE WORK

## General

### Description of the assignment

The Consultant should provide expertise in the area of the project management for successful implementation of project. The assignment of the present contract is to provide expert support through knowledge and expertise in the preparation of schedule of project activities, preparation of progress reports for the actions carried out, assistance in the preparation of the Table of expenditures and advices in the collection of the supporting documents. The Contractor will also assist on resource planning allocation and control of projects pipeline in coordination with the municipality staff.

Also, Municipality of Kocani as a beneficiary of the project “Beyond the Urban” intend to announce 2 tenders for services and supply. For the purpose successfully implementation of the above mention tender procedures Municipality of Kocani needs to be supported by the procurement expert for preparation of 2 (two) tender dossiers (one service and one supply tender procedure) in the procurement process and enable smooth implementation of planned procurements. This means that the procurement procedures need to be implemented according the EU and PRAG rules version PRAG 2022.

### Geographical area to be covered

Municipality of Kocani

### Target groups

The main target groups addressed by the Action are residents in Kocani, staff within sector for traffic planning, local public institutions, local transport operators from the business sector in the Municipality of Kocani.

## Specific work

4.2.1 Support of the project team in the implementation of the project

The assignment of the present contract is to provide expert knowledge and expertise in the preparation of schedule of project activities, preparation of progress reports for the actions carried out, assistance in the preparation of the Table of expenditures and advices in the collection of the supporting documents. The Contractor will also assist on resource planning allocation and control of projects pipeline in coordination with the municipality staff.

The expert should support in delivery of on-time scope actions and results, guidance and clarification in performance of the project activities. Assistance on resource planning allocation and control of projects pipeline in coordination with the municipality staff

Coordination actions with the municipality staff, planning of the financial resources and timing of the activities in correspondence with the procurement plan, adjustment of the actions related to the actual implementation conditions

4.2.2 Formulation of the tender dossiers for supply and service by PRAG 2022

The consultant should formulate following tender dossiers:

Single Service Tender Dossier – Development of Sustainable Urban Mobility Plan (SUMP)

Single supply Tender Dossier – Supply of equipment

## Project management

### Responsible body

The Contracting Authority is Municipality of Kocani, Republic of North Macedonia and in that capacity, it is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during project implementation. The day-to-day operational project implementation will be performed by Municipality of Kocani, Project office – which is responsible for implementation of project

### Management structure

The project “Beyond the Urban” is implemented by Creacció Agència d'Emprenedoria of Vic from Spain in partnership with Municipality of Kocani and 8 other partners. Municipality of Kocani will be the Contracting Authority responsible for regular coordination as well as coordination with the other partners and will have the overall responsibility of implementation of the project activities in Republic of North Macedonia

### Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority will provide all available information and will fully co-operate with the Consultant in order to achieve the best results. Technical information and access to the existing records, any useful information and/or documentation which may be relevant to the performance of the Contract will be provided upon request.

# LOGISTICS AND TIMING

## Location

Municipality of Kocani

## Start date & period of implementation of tasks

The intended start date is 20.03.2024 and the period of implementation of the contract will be 18 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIEMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contracting authority.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in english in one original:

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report.

# MONITORING AND EVALUATION

## Definition of indicators

- Formulated project reports

- Formulated TD for service and supply